# SPECIAL CONDITIONS FOR EUROPEAN UNION EXTERNAL ACTIONS

# Contents

These conditions amplify and supplement the general conditions governing the contract. Unless the special conditions provide otherwise, those general conditions remain fully applicable. The numbering of the articles of the special conditions is not consecutive but follows the numbering of the articles of the general conditions. Exceptionally, and with the approval of the competent European Commission departments, other clauses can be indicated to cover particular situations.

# The subject of the contract shall be:

The subject of the contract shall be the supply, delivery, unloading, installation, inspection and commissioning, Site Acceptance Testing (SAT), operator and maintenance training, warranty service and technical support during the warranty period of one (1) Jaw Crusher Machine with an Integrated Picking Station for the Re-use and Management of Construction and Demolition Waste, including all documentation, manuals and ancillary equipment required under Annex II – Technical Specifications.

of the following supplies:

One (1) Mobile Jaw Crusher Machine with an Integrated Picking Station for the Re-use and Management of Construction and Demolition Waste in 1 lot

# Order of precedence of contract documents

The following documents shall be deemed to form and be read and construed as part of this contract, in the following order of precedence:

- the main conditions;

- the special conditions;

- the general conditions (Annex I);

- the technical specifications (Annex II including clarifications before the deadline for submission of tenders);

- the technical offer (Annex III including clarifications from the tenderer provided during tender evaluation);

- the budget breakdown (Annex IV);

- specified forms and other relevant documents (Annex V);

The various documents making up the contract shall be deemed to be mutually explanatory; in cases of ambiguity or divergence, they shall prevail in the order in which they appear above. Addenda shall have the order of precedence of the document they are amending.

Article 1A – Definitions

For the purposes of this Contract, the following definitions shall apply:

(a) "Place of Acceptance" means the final installation and operating site designated by the Contracting Authority where delivery, unloading, installation, inspection and commissioning, Performance Testing, Site Acceptance Test (SAT), Provisional Acceptance and Final Acceptance are carried out.

(b) "Preliminary Technical Acceptance (PTA)" means the verification of the identity, completeness and conformity of the delivered equipment, components, accessories, spare parts, manuals, certificates and technical documentation against the Contractor's Technical Offer and Annex II – Technical Specifications. PTA shall not constitute Provisional Acceptance.

(c) "Mechanical Inspection and Commissioning" means the verification of the correct assembly, installation and mechanical operation of the crusher, integrated picking station, conveyors, magnetic separator, water spraying system, hydraulic systems and all associated mechanical components.

(d) "Electrical and Control Inspection and Commissioning" means the verification of the diesel engine, electrical systems, control panels, sensors, emergency stop systems, safety interlocks and calibration of operating parameters.

(e) "Functional Testing" means dry-run testing without material to verify the operation of all moving components, controls, alarms, safety devices and operational functions.

(f) "Performance Testing" means testing carried out using actual construction and demolition waste supplied by the Contracting Authority in order to verify compliance with all minimum performance requirements specified in Annex II – Technical Specifications, including processing capacity, output granulation and operation of all major systems.

(g) "Site Acceptance Test (SAT)" means the contractual testing and verification procedure performed following successful completion of Performance Testing in order to confirm the complete operational readiness of the equipment and its conformity with all contractual requirements. The Site Acceptance Test (SAT) shall be conducted in accordance with the SAT Engineering Acceptance Report (SAT EAR) forming part of the Tender Dossier.

(h) "Deficiency Register" or "Punch List" means the document prepared during the SAT identifying deficiencies, defects, omissions or outstanding items requiring corrective action before Final Acceptance.

(i) "Category A (Critical) Deficiency" means any deficiency affecting safety, functionality, operational use, contractual performance or compliance with the minimum technical requirements of the Contract. Category A deficiencies shall prevent Provisional Acceptance.

(j) "Category B (Major) Deficiency" means any deficiency which does not constitute a Category A deficiency but materially affects operation, reliability, documentation, training or contractual compliance. Category B deficiencies shall normally prevent Provisional Acceptance until corrected.

(k) "Category C (Minor) Deficiency" means any deficiency of an administrative, documentary, cosmetic or minor operational nature which does not affect safety, functionality or contractual performance. Category C deficiencies may permit Conditional Provisional Acceptance.

(l) "Conditional Provisional Acceptance" means a recommendation of the Acceptance Commission that the equipment may enter operational use despite the existence of outstanding Category C deficiencies, provided that such deficiencies are corrected within the deficiency correction period specified in the Contract.

(m) "Provisional Acceptance" means the formal contractual acceptance of the equipment evidenced by issuance of the Certificate of Provisional Acceptance in accordance with Article 31 of the Special Conditions.

(n) "Final Acceptance" means confirmation by the Contracting Authority that all deficiencies identified during Provisional Acceptance have been remedied and all contractual obligations required for release of the final payment have been fulfilled.

(o) "Critical Failure" means a malfunction that renders the equipment wholly inoperable, unsafe to operate or incapable of performing its intended function.

(p) "Major Failure" means a malfunction that significantly reduces the operational performance of the equipment but does not render it completely inoperable.

(q) "Minor Failure" means a malfunction or defect that does not materially affect the safe operation or contractual performance of the equipment.

(r) "Acceptance Commission" means the body appointed by the Contracting Authority to witness, supervise, verify and evaluate inspections, tests, commissioning activities, Performance Testing, SAT procedures and acceptance activities under the Contract.

(s) "Deficiency Correction Period" means the period of up to thirty (30) calendar days following Provisional Acceptance during which identified deficiencies, defects and outstanding items may be corrected by the Contractor.

Article 2	Language of the contract

2.1	The language used shall be English.

Article 4	Communications

4.1	Communication details

4.4	Communication via electronic exchange system (EES)

An electronic system will be used by the contracting authority and the contractor for all stages of implementation including, inter alia, management of the contract (amendments and administrative orders), reporting (including reporting on results) and payments. The contractor will be required to register in and use the appropriate electronic exchange system to allow for the e-management of the contract.

After the entry into force of this contract, at any time during its course the contracting authority may formally notify in writing the contractor that certain communications will be made by electronic means through the EU Funding & Tenders Portal (the Portal), in accordance with the Portal Terms and Conditions and using the forms and templates provided there. The Portal can be accessed via the following URL: https://ec.europa.eu/info/funding-tenders/opportunities/portal/ The notification shall indicate whether all or only certain communications under the contract will take place through the Portal. The notification shall have full legal effect from the date specified therein, which shall allow a reasonable period of time for the contractor to complete all necessary steps to have access to the Portal. The activation of the use of the Portal shall be at no additional cost for the contracting authority.

If the use of the Portal is activated, any communication covered by the activation notification related to the implementation of this contract shall be made through the Portal (except if explicitly instructed otherwise by the contracting authority or if communication via the Portal is hindered by factors beyond the control of the parties).

Communications by contractors through the Portal must be made by persons authorised according to the Portal Terms and Conditions. For naming the authorised persons to use the Portal, each contractor must designate before the date of effect of the activation notification a ‘legal entity appointed representative (LEAR)’. The role and tasks of the LEAR are stipulated in their appointment letter (see Portal Terms and Conditions).

If the communication via the Portal is hindered, instructions will be provided by the contracting authority by email and may also be published on the Portal.

During the course of the contract, the contracting authority reserve(s) the right to further extend the coverage of the communications made through the Portal (if its use has been already activated) or to activate the use of other electronic exchange systems, at no additional cost for the contracting authority.

In case of discrepancy between the clauses of the Portal Terms and Conditions or Terms and Conditions of other electronic exchange system and the clauses of this contract, the clauses of this contract (including its annexes) shall prevail.

4.5 & 4.6	Mail or email communication

If communications through the Portal have not been activated or a certain type of communication is not yet supported by the Portal, communications will be sent via email, or, exceptionally, on paper, via mail services, to the following addresses, until communications via the Portal are activated.

For the purpose of this contract, mail or email communications must be sent to the following addresses:

Contracting authority:

Full name: City of Skopje

Full official address: Boulevard Ilinden 82, 1000 Skopje, North Macedonia

Email:  reconstruct@skopje.gov.mk

Contractor (or leader in the case of a joint tender):

Full name

Function

Company name

Full official address

Email: complete

Article 6	Subcontracting

6.3	n/a

Article 7	Supply of documents

The Contractor shall supply, at no additional cost to the Contracting Authority, all documents, manuals, drawings and certificates necessary for the delivery, installation, inspection and commissioning, operation, maintenance and safe use of the equipment.

As a minimum, the Contractor shall provide:

(a) Operator's Manual and User Instructions;

(b) Maintenance and Service Manual;

(c) Spare Parts Catalogue, including part numbers and exploded diagrams;

(d) Electrical diagrams, hydraulic schematics and control system drawings;

(e) Technical brochures, manufacturer's data sheets and product documentationts;

(f) CE Declaration of Conformity and all applicable certificates of compliance;

(g) Commissioning procedures, inspection checklists and testing protocols necessary for mechanical, electrical and functional inspection and commissioning of the equipment;

(h) Proposed Site Acceptance Test (SAT) methodology, acceptance procedures and supporting documentation necessary for execution of the Site Acceptance Test in accordance with the Contract;

(i) Warranty certificates and contact details for warranty support, technical assistance and after-sales service;

(j) Training materials for operators and maintenance personnel;

(k) Recommended preventive maintenance schedule, lubrication schedule and consumables list;

(l) Recommended spare parts list, including indicative replacement intervals and service recommendationsals.

All documents shall be supplied in English and in Macedonian language. The Contractor shall provide one (1) original hard copy and one (1) electronic copy in searchable PDF format and, where applicable, editable formats.

The Contracting Authority shall review the documents for completeness and compliance with the Contract and may request corrections, clarifications or additional information where necessary. The Contractor shall provide the requested revisions within five (5) working days of receipt of the Contracting Authority's request.

The approval of documents by the Contracting Authority shall not relieve the Contractor of any of its obligations under the Contract, nor shall it constitute acceptance of the equipment or waiver of any contractual rights of the Contracting Authority.

Submission of the documents specified in this Article shall constitute a condition for Provisional Acceptance of the equipment.

Article 8	Assistance with local regulations

The Contracting Authority shall, where appropriate and upon reasonable request by the Contractor, provide reasonable assistance in facilitating contacts with the competent national authorities in relation to permits, licences, customs procedures and other administrative formalities necessary for the implementation of the Contract.

Notwithstanding the above, the prime and ultimate responsibility for obtaining all permits, licences, authorisations, approvals, customs clearances and other administrative requirements necessary for the execution of the Contract shall rest solely with the Contractor and shall be at the Contractor's own risk and expense.

Given that the supplies are to be delivered on a DDP (Delivered Duty Paid – Incoterms® 2020) basis, the Contractor shall be fully responsible for all import and export formalities, customs procedures and any other requirements necessary to deliver the equipment to the place of acceptance in accordance with the Contract.

The foregoing shall be without prejudice to any tax or customs exemptions applicable to the Contract under the Financing Agreement and the applicable legislation of the Republic of North Macedonia.

The Contractor shall comply with all applicable laws and regulations of the Republic of North Macedonia, including customs, import and export regulations, as amended from time to time, and shall keep the Contracting Authority informed of the status of all permits and licences relevant to the implementation of the Contract.

The Contractor shall promptly inform the Contracting Authority of any circumstances that may affect the timely obtaining of permits, licences, authorisations or customs clearances and may impact the implementation of the Contract.

If the Contractor is late in applying for, or fails to obtain, any permit, licence, authorisation or customs clearance required for the execution of the Contract, the Contractor shall not be entitled to any extension of the Period of Implementation, additional payment or any other compensation arising therefrom.

Any costs arising from delays in customs clearance, import procedures, storage, demurrage, handling or similar administrative matters shall be borne exclusively by the Contractor.

Article 9	General obligations

9.9	The Contractor shall comply with the Communication and Visibility Requirements for EU-funded external actions, as laid down and published by the European Commission.

The Contracting Authority shall be responsible for all communication and visibility activities related to the Contract and the RE-CONSTRUCT Project, including the placement of any permanent or temporary visibility stickers, plaques, signs or other communication materials on the supplied equipment.

The Contractor shall cooperate with the Contracting Authority and provide reasonable assistance for communication, visibility and reporting purposes, including:

(a) allowing access to the equipment for visibility activities;

(b) providing, upon request, photographic documentation of the delivery, installation, inspection and commissioning and Site Acceptance Test (SAT) activities;

(c) providing factual information reasonably required by the Contracting Authority for reporting and visibility purposes.

The Contractor shall not issue any press release, public statement or communication material relating to the Contract without the prior written approval of the Contracting Authority.

Compliance with the obligations set out in this Article shall be deemed included in the Contract Price and shall not entitle the Contractor to any additional payment.

Article 10	Origin

## 10.1	All goods purchased under the Contract shall comply with the rules of origin applicable to the IPA II programme, in accordance with Regulation (EU) No 236/2014, Regulation (EU) No 231/2014 and Annex A2a to the Practical Guide. For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured. The origin of the goods must be determined according to the EU Customs Code or to the relevant international agreement applicable.

## A certificate of origin for the goods must be provided by the contractor at the latest when it requests provisional acceptance of the goods. Failure to comply with this condition may result in the termination of the contract and/or suspension of payment.

Article 11	Performance guarantee

11.1	The amount of the performance guarantee shall be 10% of the total contract price, including any amounts stipulated in addenda to the contract.

11.2  The Performance Guarantee shall remain valid throughout the Period of Implementation and until all contractual obligations required under the Contract have been fulfilled. It shall be released by the Contracting Authority following Final Acceptance and fulfilment of all contractual obligations in accordance with these Special Conditions.

Article 12	Liabilities and insurance

12.1(a)	The Contractor shall be fully liable for any loss of, or damage to, the supplies, equipment, components and ancillary materials until Provisional Acceptance has been granted in accordance with the Contract.

The Contractor shall bear all costs of repair, replacement, transportation, reinstallation, recommissioning and retesting of any damaged or lost supplies.

For the avoidance of doubt, successful delivery, unloading, installation or commissioning shall not transfer the risk of loss or damage to the Contracting Authority. The transfer of risk shall occur only upon signature of the Provisional Acceptance Certificate following successful completion of commissioning, performance testing and the Site Acceptance Test (SAT).

12.1(b)	The Contractor shall be liable for any damage caused to the property of the Contracting Authority, its personnel, third parties or the environment arising out of or in connection with the execution of the Contract, including delivery, unloading, installation, commissioning, testing and Site Acceptance Test (SAT) activities.

The Contractor shall be responsible for all costs of remediation, clean-up and restoration arising from any environmental damage caused by its personnel, subcontractors, equipment or activities during the execution of the Contract.

12.2(a), paragraph 1	By derogation from Article 12.2(a), paragraph 1, of the General Conditions, the Contractor shall ensure that itself, its personnel, its subcontractors and any person for whom the Contractor is responsible are adequately insured with insurance companies recognised on the international insurance market prior to commencement of the implementation of the Contract and throughout the entire Period of Implementation and warranty obligations where applicable.

12.2(a), paragraph 2	By derogation from Article 12.2(a), paragraph 2, of the general conditions it is no later than fifteen (15) calendar days following contract signature and in any event prior to the commencement of delivery of the supplies that the contractor shall provide the contracting authority with all cover notes and/or insurance certificates showing that the contractor's obligations relating to insurance are fully respected.

12.2(b), paragraph 2	Given that the supplies are delivered on a DDP (Delivered Duty Paid – Incoterms® 2020) basis, the Contractor shall maintain adequate transport and cargo insurance covering the full replacement value of the equipment and all ancillary components from the point of dispatch until Provisional Acceptance.

The insurance shall include, as a minimum, coverage for:

(a) loading and unloading operations;

(b) international and domestic transport;

(c) intermediate storage and handling;

(d) theft, vandalism and malicious damage;

(e) accidental damage and total loss;

(f) wetting, contamination and weather-related damage;

(g) damage during installation, commissioning and testing activities;

(h) third-party liability arising from delivery, unloading, installation and commissioning activities;

(i) erection, installation and commissioning all-risks insurance, including accidental damage occurring during assembly, testing and Site Acceptance Test (SAT) activities.

Any loss of or damage to the equipment occurring prior to Provisional Acceptance shall be remedied by the Contractor at its own cost and without any extension of the Period of Implementation, unless otherwise agreed by the Contracting Authority in writing.

Article 13	Programme of implementation of the tasks

13.2	The Contractor shall submit to the Contracting Authority, within fifteen (15) calendar days from the commencement date of the implementation period communicated by administrative order, an accurate and detailed Programme of Implementation as stipulated in Article 13.1 of the General Conditions.

The Programme of Implementation shall indicate, as a minimum, the planned dates for:

(a) completion of manufacture and factory preparation;

(b) shipment and transport;

(c) customs clearance, where applicable;

(d) arrival in the Republic of North Macedonia;

(e) arrival at the place of acceptance;

(f) unloading and installation;

(g) inspection and commissioning;

(h) Site Acceptance Test (SAT);

(i) operator and maintenance training;

(j) submission of all contractual documentation, including manuals, certificates and certificate of origin;

(k) Provisional Acceptance.

The Programme of Implementation shall clearly identify the tasks and sub-tasks for each phase of the Contract, the interdependencies between activities, key milestones and the resources, personnel and equipment that will be provided by the Contractor for their implementation.

The Programme of Implementation shall reflect all requirements of Annex II – Technical Specifications and shall be accompanied by a duly completed Annex VI – Work Plan.

The Contracting Authority shall make comments and/or objections concerning the Programme of Implementation within fourteen (14) calendar days of its submission. Such comments and/or objections shall be deemed accepted by the Contractor unless the Contractor submits written observations, including by electronic means capable of producing a written record, within seven (7) calendar days of their receipt.

The absence of comments and/or objections from the Contracting Authority within the fourteen (14) calendar days referred to above shall be deemed to constitute approval of the Programme of Implementation.

The Contractor shall promptly update the Programme of Implementation whenever circumstances arise that may affect the timely execution of the Contract and shall submit the revised Programme to the Contracting Authority for approval.

Where the supplied equipment is intended for use on public roads and is subject to homologation requirements under the applicable legislation of the Republic of North Macedonia, the Contractor shall provide a Certificate of Conformity and all technical documentation necessary for registration and homologation of the equipment, including, where applicable, axle load calculations, dimensions, technical specifications and quality assurance documentation.

Where the supplied equipment is not subject to homologation requirements, the Contractor shall provide all applicable manufacturer's certificates, declarations of conformity, technical documentation and quality assurance documentation required under Annex II – Technical Specifications and for Provisional Acceptance of the equipment.

Article 14	Contractor’s drawings

14.1	The Contractor shall submit to the Contracting Authority all drawings, manuals, certificates and technical documentation necessary for the delivery, installation, commissioning, operation, maintenance and safe use of the equipment.

As a minimum, the Contractor shall provide:

(a) general arrangement drawings of the supplied equipment;

(b) layout drawings showing the dimensions and operational clearances required for installation and operation;

(c) electrical diagrams, wiring diagrams and control system drawings;

(d) hydraulic and pneumatic schematics, where applicable;

(e) technical data sheets and manufacturer's specifications;

(f) spare parts catalogues, including part numbers and exploded drawings;

(g) operation and maintenance manuals;

(h) preventive maintenance schedules and lubrication charts;

(i) inspection and commissioning procedures and testing protocols;

(j) Proposed Site Acceptance Test (SAT) methodology, manufacturer's testing procedures and supporting technical documentation;

(k) certificates of conformity, declarations of conformity and all certificates required under the Contract and Annex II – Technical Specifications;

(l) training materials for operators and maintenance personnel.

All documentation shall be supplied in English and in Macedonian language, unless otherwise agreed by the Contracting Authority.

The Contractor shall provide one (1) original hard copy and one (1) electronic copy in searchable PDF format and, where applicable, editable electronic formats.

The Contracting Authority may review the submitted drawings and documentation and request corrections, clarifications or additional information where necessary for the implementation of the Contract. Such review shall not relieve the Contractor of any contractual obligations or responsibilities.

The Contractor shall provide any requested revisions or additional documentation within five (5) working days of receipt of the Contracting Authority's request.

The submission of all drawings, manuals, certificates and technical documentation required under this Article and Annex II – Technical Specifications shall constitute a condition for Provisional Acceptance of the equipment.

Article 15	Sufficiency of tender prices

The price of the supplies shall be that shown on the financial offer (specimen in Annex IV).

15.1 By submitting its tender, the Contractor shall be deemed to have satisfied itself as to the correctness and sufficiency of its tender price.

The Contract Price shall be deemed to include all costs, expenses, risks and obligations necessary for the complete and proper execution of the Contract in accordance with the Main Conditions, Special Conditions, General Conditions, Annex II – Technical Specifications and the Contractor's Technical Offer.

Without limitation, the Contract Price shall be deemed to include:

(a) manufacture, supply and factory preparation of the equipment;

(b) packing, loading, transport, insurance and delivery on a DDP (Delivered Duty Paid – Incoterms® 2020) basis;

(c) export and import formalities, customs procedures, permits, licences and all related administrative requirements;

(d) unloading, installation and commissioning of the equipment;

(e) Site Acceptance Test (SAT), performance testing and all retesting required to demonstrate compliance with the Contract;

(f) operator and maintenance training;

(g) provision of all drawings, manuals, certificates, technical documentation and certificates of origin required under the Contract;

(h) warranty service and technical support obligations during the warranty period;

(i) all labour, personnel, equipment, tools, consumables, travel, accommodation, subsistence and other resources required for implementation of the Contract;

(j) all taxes, duties, fees, charges and expenses, except for any tax exemptions expressly applicable under the Financing Agreement and the applicable legislation of the Republic of North Macedonia.

The Contractor shall not be entitled to any additional payment, price adjustment or compensation arising from any omission, miscalculation, misunderstanding, failure to inspect the contractual requirements, underestimation of costs or difficulties encountered in the execution of the Contract.

The itemised indicative price lists for spare parts, consumables and after-sales services submitted with the tender are provided for information purposes only and shall not form part of the Contract Price or the financial evaluation of tenders.

Article 16	Tax and customs arrangements

16.1 The supplies shall be delivered on a DDP (Delivered Duty Paid – Incoterms® 2020) basis to the place of acceptance specified in the Contract.

The Contractor shall be responsible for all taxes, duties, customs formalities, import and export clearances, permits, licences, fees and other charges necessary for the execution of the Contract, except for any tax or customs exemptions expressly applicable under the Financing Agreement and the applicable legislation of the Republic of North Macedonia.

The Contractor shall take all necessary measures to ensure the proper application of any tax or customs exemptions communicated by the Contracting Authority and shall provide all documentation reasonably required for the implementation of such exemptions.

No additional payment or compensation shall be due to the Contractor in respect of taxes, duties, customs procedures or other charges that have not been expressly identified as exempt under the applicable legal framework.

Article 17	Patents and licences

17.1	No derogation from Article 17 of the General Conditions shall apply.

For the avoidance of doubt, the Contractor warrants that all licences, patents, software rights, intellectual property rights and other proprietary rights necessary for the operation, maintenance and intended use of the supplied equipment have been duly obtained and are included in the Contract Price.

The Contractor shall indemnify and hold harmless the Contracting Authority against any claims, actions, proceedings, damages, costs or expenses arising from any alleged infringement of patents, licences, trademarks, copyrights, software rights or other intellectual property rights related to the supplies provided under the Contract.

Any software licences required for the operation, monitoring, diagnostics or maintenance of the equipment shall be supplied to the Contracting Authority on a perpetual, non-exclusive and royalty-free basis unless otherwise expressly provided in the Technical Specifications.

Article 18	Delivery order

18.2	The Contracting Authority shall inform the Contractor by administrative order of the date on which the implementation of the Contract shall commence.

The administrative order shall not be issued until the Contractor has fulfilled all contractual conditions precedent to commencement of implementation, including the submission of the Performance Guarantee and the insurance certificates required under the Contract.

The Period of Implementation of the Contract shall begin on the date specified in the administrative order.

No delivery, installation, commissioning, Site Acceptance Test (SAT) activities or other contractual obligations requiring commencement of implementation shall be considered to have started prior to the date specified in the administrative order, unless otherwise expressly agreed in writing by the Contracting Authority.

Article 19	Period of implementation of the tasks

19.1	The Contractor shall complete the delivery, unloading, installation, Mechanical Inspection and Commissioning, Electrical and Control Inspection and Commissioning, Functional Testing, Performance Testing, Site Acceptance Test (SAT), operator and maintenance training, and submission of all contractual documentation required for Provisional Acceptance within ninety (90) calendar days from the date specified in the administrative order referred to in Article 18.

Where, following completion of the Site Acceptance Test (SAT), the Acceptance Commission recommends Conditional Provisional Acceptance due exclusively to outstanding Category C (Minor) deficiencies, the Contractor shall remedy such deficiencies within a Deficiency Correction Period of up to thirty (30) calendar days, unless a shorter period is specified by the Contracting Authority.

Accordingly, the maximum Period of Implementation of the Contract shall be one hundred and twenty (120) calendar days, comprising:

- Phase 1: up to 90 calendar days for completion of all contractual implementation activities required for the issue of the Certificate of Provisional Acceptance (C11A); and

- Phase 2 (where applicable): up to 30 calendar days for correction of Category C (Minor) deficiencies identified during Conditional Provisional Acceptance.

No extension of the implementation period shall be granted except in accordance with the provisions of the General Conditions and the Special Conditions of the Contract.

Article 24	Quality of supplies

24.2	A Preliminary Technical Acceptance shall be carried out upon delivery of the equipment to verify that the supplies delivered correspond to the requirements of the Contract and Annex II – Technical Specifications.

The Preliminary Technical Acceptance shall include, as a minimum:

(a) verification of the identity and quantity of the supplied equipment and components;

(b) verification of the completeness of the delivery, including ancillary equipment and accessories;

(c) visual inspection for damage, defects or missing parts;

(d) verification of the availability of certificates, manuals, drawings and technical documentation required under the Contract;

(e) verification that the equipment corresponds to the specifications, configuration and performance characteristics offered by the Contractor.

The Preliminary Technical Acceptance shall be documented by means of a Preliminary Technical Acceptance Record signed by the Parties.

The successful completion of the Preliminary Technical Acceptance shall not constitute Provisional Acceptance, shall not transfer the risk of loss or damage to the Contracting Authority and shall not release the Contractor from any obligations relating to installation, commissioning, Site Acceptance Test (SAT), performance testing, training, submission of documentation or warranty obligations.

The Preliminary Technical Acceptance shall not give rise to any payment entitlement and shall not prejudice the right of the Contracting Authority to refuse Provisional Acceptance in the event of non-compliance with the Contract or Annex II – Technical Specifications.

Article 25	Inspection and testing

25.2	The Contracting Authority and its authorized representatives shall have the right to inspect and test the supplies at any stage of manufacture, preparation, delivery, installation, commissioning and acceptance in order to verify compliance with the Contract and Annex II – Technical Specifications.

Prior to commencement of the Site Acceptance Test (SAT), the Acceptance Commission shall verify that the Pre-SAT Readiness requirements specified in the SAT Engineering Acceptance Report (SAT EAR) have been satisfactorily completed.

Inspections and tests may be carried out, where applicable:

(a) at the manufacturer's premises;

(b) during preparation for shipment;

(c) upon delivery at the place of acceptance;

(d) during unloading and installation;

(e) during commissioning activities;

(f) during Site Acceptance Test (SAT) activities;

(g) at any other location reasonably required to verify compliance with the Contract.

The inspection and testing programme shall include, as a minimum, the following stages:

(i) Preliminary Technical Acceptance (PTA)

Verification of the identity, completeness and conformity of the delivered equipment, components, accessories, spare parts, manuals, certificates and technical documentation and confirmation that the supplies correspond to the Contractor's Technical Offer and Annex II – Technical Specifications.

Preliminary Technical Acceptance (PTA) shall not constitute Provisional Acceptance, transfer of risk or release of the Contractor from any obligations under the Contract.

(ii) Mechanical Inspection and Commissioningg

Shall be carried out in accordance with the Contract and the approved Commissioning Procedures and shall verify the correct installation and mechanical operation of the supplied equipment. It consists of, but it is not limited to: verification of the assembly and installation of the crusher and integrated picking station, conveyors, magnetic separator, water spraying system, hydraulic systems and all other components and connections.

(iii) Electrical and Control Inspection and Commissioning

Verification of the diesel engine, electrical systems, control panels, sensors, emergency stop systems and calibration of operating parameters.

(iv) Functional Testing

Dry-run testing without material, testing of all moving components and verification of safety systems, alarms and operational functions.

(v) Performance Testing

Performance Testing shall be carried out in accordance with the Site Acceptance Test (SAT) Engineering Acceptance Report (SAT EAR) forming part of the Tender Dossier and using the Contractor's approved inspection and commissioning procedures, proposed testing methodology and supporting technical documentation submitted under Article 7:

- required processing capacity;

- output granulation;

- operation of the integrated picking station;

- operation of the magnetic separator;

- operation of conveyor systems;

- operation of dust suppression and water spraying systems;

- operation of the mobility system;

- operation of all safety systems;

- operation of all auxiliary systems.

Performance Testing shall be carried out in accordance with the approved SAT Protocol.

Successful completion of Performance Testing shall constitute a prerequisite for commencement of the Site Acceptance Test (SAT).

(vi) Site Acceptance Test (SAT)

The Site Acceptance Test (SAT) shall be documented in the SAT Engineering Acceptance Report (SAT EAR), which shall constitute the official record of the inspections, testing activities, observations, measurements, deficiencies and recommendations arising from the acceptance process.

It shall verify the complete operational readiness of the equipment and its conformity with all contractual requirements and shall include, as a minimum:

(a) verification of successful completion of inspection and commissioning activities;

(b) verification of successful completion of Performance Testing;

(c) confirmation of the operational status of all safety systems and emergency functions under site operating conditions;;

(d) verification of documentation, manuals and certificates;

(e) verification of completion of training activities;

(f) verification of the initial spare parts package;

(g) preparation of the Deficiency Register (Punch List), classification of deficiencies and recommendation regarding:

- Provisional Acceptance;

- Conditional Provisional Acceptance; or

- Refusal of Provisional Acceptance.

Conditional Provisional Acceptance may only be recommended where the identified deficiencies are minor in nature, do not affect the safe operation, functionality or minimum performance requirements of the equipment and can be remedied within the deficiency correction period specified in the Contract.

Deficiencies identified during the Site Acceptance Test (SAT) shall be classified as follows:

Category A (Critical) Deficiency:

A deficiency affecting safety, functionality, operational use, contractual performance or compliance with the minimum technical requirements of the Contract. Category A deficiencies shall prevent Provisional Acceptance.

Category B (Major) Deficiency:

A deficiency which does not constitute a Category A deficiency but materially affects operation, reliability, documentation, training or contractual compliance. Category B deficiencies shall normally prevent Provisional Acceptance until corrected.

Category C (Minor) Deficiency:

A deficiency of an administrative, documentary, cosmetic or minor operational nature which does not affect safety, functionality or contractual performance. Category C deficiencies may permit Conditional Provisional Acceptance.

Only Category C deficiencies remain outstanding at the time of Conditional Provisional Acceptance.

Successful completion of the Site Acceptance Test (SAT) shall constitute a prerequisite for issuance of the Certificate of Provisional Acceptance in accordance with Article 31 of the Special Conditions.

The Contractor shall provide all personnel, tools, calibrated measuring instruments, test equipment, consumables, manufacturer's documentation, commissioning procedures, proposed testing methodology, technical assistance and other resources necessary for carrying out the inspections, commissioning activities, Performance Testing and the Site Acceptance Test (SAT).

The Contractor shall participate in the execution of the Site Acceptance Test (SAT) and shall provide all technical measurements, operating data, test results, calibration certificates and supporting technical information reasonably required by the Acceptance Commission for completion of the SAT Engineering Acceptance Report (SAT EAR).

The SAT Engineering Acceptance Report (SAT EAR), forming part of the Tender Dossier, shall be completed by the Acceptance Commission on the basis of the inspections and tests carried out jointly with the Contractor and shall constitute the official contractual record of the acceptance process.

The SAT Engineering Acceptance Report shall include, as applicable

(a) Mechanical Inspection Record;

(b) Electrical Inspection Record;

(c) Functional Testing Record;

(d) Performance Testing Record;

(e) Fuel Consumption Verification;

(f) Output Granulation Verification;

(g) Deficiency Register (Punch List), where applicable.

(h) Committee Recommendation

The SAT Engineering Acceptance Report and all records forming part thereof shall be signed by the Contractor and the authorised representatives of the Contracting Authority.

The Contracting Authority may appoint an Acceptance Commission and/or external technical experts to witness, supervise and verify any inspection, test or acceptance activity under this Article.

The Contractor shall provide reasonable prior notice of all inspections and tests and shall ensure that the Contracting Authority and its authorised representatives have full access to the equipment and testing activities.

For the avoidance of doubt, completion of any inspection, test, commissioning activity, Performance Testing or Site Acceptance Test (SAT) shall not by itself constitute Provisional Acceptance, transfer of risk or release of the Contractor from any obligations under the Contract. Provisional Acceptance shall be deemed to occur only upon issuance of the Certificate of Provisional Acceptance in accordance with Article 31 of the Special Conditions.

Where any inspection or test demonstrates non-compliance with the Contract or Annex II – Technical Specifications, the Contracting Authority may require repair, replacement, adjustment, repetition of testing or any other corrective measures necessary to achieve compliance. All costs associated with corrective actions and retesting shall be borne exclusively by the Contractor.

Failure to successfully complete Performance Testing, failure to successfully complete the Site Acceptance Test (SAT), or failure to demonstrate compliance with the minimum performance requirements specified in Annex II – Technical Specifications shall entitle the Contracting Authority to:

(a) refuse Provisional Acceptance;

(b) require corrective actions;

(c) require repair, replacement or adjustment of the equipment;

(d) require repetition of any inspection or test;

(e) suspend payment of the ninety per cent (90%) instalment; and

(f) reject the equipment where non-compliance materially affects the achievement of the minimum technical requirements of the Contract.

All costs and risks associated with corrective actions, repairs, replacements and re-testing shall be borne exclusively by the Contractor.

Following completion of the corrective actions, the Contractor shall make the equipment available for such re-inspections, re-testing or performance verification as the Acceptance Commission considers necessary in accordance with the SAT Engineering Acceptance Report (SAT EAR).

All records generated during Mechanical Inspection and Commissioning, Electrical and Control Inspection and Commissioning, Functional Testing, Performance Testing and the Site Acceptance Test (SAT) shall form integral parts of the SAT Engineering Acceptance Report (SAT EAR) and shall constitute the technical evidence supporting the Acceptance Commission's recommendation regarding the issue of the Provisional Acceptance Certificate (C11A).

Article 26	General principles

26.1 Payments shall be made in EUR

Pre-financing is not applicable to this contract

Payments shall be authorised and made by City of Skopje
Sector for Finance
Ilinden Boulevard No. 82
1000 Skopje
Republic of North Macedonia.

The issue of the first payment shall not affect the validity of the Performance Guarantee, which shall remain in force until released in accordance with Article 11 of these Special Conditions.

26.3	(a) The first payment of ninety per cent (90%) of the Contract Price shall be made within ninety (90) days following receipt by the Contracting Authority of:

(i) an admissible invoice;

(ii) the application for the certificate of Provisional Acceptance;

(iii) the certificate of origin for the supplies delivered, where applicable; and

(iv) all supporting documents required under Article 26.5(a).

The first payment of ninety per cent (90%) of the Contract Price shall become due only upon issuance of the Certificate of Provisional Acceptance in accordance with Article 31 of the Special Conditions.

(b) The final payment of ten per cent (10%) of the Contract Price shall be made within ninety (90) days following receipt by the Contracting Authority of:

(i) an admissible invoice; and

(ii) all supporting documents required under Article 26.5(b), including confirmation that all deficiencies identified during Provisional Acceptance have been remedied and all outstanding contractual obligations required for release of the final payment have been fulfilled.

For the purposes of Article 28 of the General Conditions, the payment periods referred to above shall apply separately to each payment.

26.5	In order to obtain payments, the Contractor shall submit to the authority referred to in paragraph 26.1 above:

(a) For the first payment of ninety per cent (90%) of the Contract Price:

(i) the invoice;

(ii) the Certificate of Provisional Acceptance issued in accordance with Article 31 of the Special Conditions;

(iii) the certificate of origin for the supplies delivered;

(iv) the completed SAT Engineering Acceptance Report (SAT EAR), demonstrating successful completion of the Mechanical Inspection and Commissioning, Electrical and Control Inspection and Commissioning, Safety Inspection, Functional Testing, Performance Testing and the Site Acceptance Test (SAT), together with the Acceptance Commission's recommendation supporting the issue of the Certificate of Provisional Acceptance;;

(v) evidence of completion of delivery, unloading, installation, submission of all documentation required up to the date of Provisional Acceptance and completion of all operator and maintenance training activities.

(b) For the final payment of ten per cent (10%) of the Contract Price:

(i) the invoice;

(ii) evidence of submission of all contractual documentation, manuals, certificates and other documents required under the Contract;

(iii) confirmation that all deficiencies, defects and outstanding items identified during Provisional Acceptance have been fully remedied to the satisfaction of the Contracting Authority, confirmed by the Contracting Authority on the basis of the Contractor's completion of the outstanding obligations.;

(iv) any other documents expressly required under the Contract for release of the final payment.

The final payment of ten per cent (10%) of the Contract Price shall be made following confirmation by the Contracting Authority that all deficiencies identified during Provisional Acceptance have been remedied and all outstanding contractual obligations required for release of the final payment have been fulfilled. The final payment shall not be conditional upon the expiry of the warranty period.

26.9 	No price revision shall apply under this Contract. The Contract Price shall be fixed and not subject to adjustment.

26.10 Any payment may be offset against outstanding debts of any consortium member.

Article 28	Delayed payments

28.2	By derogation from Article 28.2 of the general conditions, once the deadline laid down in Article 26.3 has expired, the contractor shall, upon demand, be entitled to late-payment interest at the rate and for the period mentioned in the general conditions. The demand must be submitted within two months of receiving late payment.

Article 29	Delivery

29.1 	The Incoterm applicable shall be DDP

29.3	The Contractor shall ensure that all supplies are suitably packed, protected, secured and marked to prevent loss, damage, deterioration, corrosion or contamination during loading, transport, storage, unloading and installation.

All exposed components, electrical systems, hydraulic connections and sensitive equipment shall be adequately protected against moisture, dust, vibration, impact, corrosion and adverse weather conditions.

Packaging shall be suitable for international transport and, where applicable, intermediate storage and handling operations.

The Contractor shall be responsible for all damage resulting from inadequate or defective packaging.

The packaging shall become the property of the recipient subject to environmental considerations.

29.4	The place of acceptance of the supplies shall be

Public Enterprise Drisla, Skopje, Republic of North Macedonia,

or another final installation site within the administrative territory of the City of Skopje designated by the Contracting Authority in the Delivery Order.

For the purposes of this Contract, the place of acceptance shall be the location where delivery, unloading, installation, commissioning, Performance Testing, Site Acceptance Test (SAT) and Provisional Acceptance are carried out.

29.5	Each delivery shall be accompanied, as a minimum, by the following documents:

(a) Delivery Note;

(b) Packing List;

(c) Commercial Invoice;

(d) Certificate of Origin;

(e) Certificate of Conformity and/or Declaration of Conformity, where applicable;

(f) CE Declaration of Conformity, where applicable;

(g) Operation and Maintenance Manuals;

(h) Spare Parts Catalogue;

(i) Warranty Certificate;

(j) Transport documents, including CMR, Bill of Lading or equivalent documents, where applicable;

(k) Any other documents required under Annex II – Technical Specifications.

29.6 	All packages, crates and transport units shall be clearly marked in English and Macedonian language and shall include, as a minimum:

(a) Contract reference number;

(b) Name of the Contracting Authority;

(c) Name of the Contractor;

(d) Description of contents;

(e) Package number and total number of packages;

(f) Gross and net weight;

(g) Handling instructions;

(h) Centre of gravity markings and lifting points, where applicable;

(i) Safety warnings and storage requirements, where applicable.

29.7 	The absence of any document or marking required under this Article may constitute grounds for refusal of delivery, Preliminary Technical Acceptance or Provisional Acceptance until the deficiency has been remedied by the Contractor.

Article 31	Provisional acceptance

The certificate of provisional acceptance must be issued using the template in Annex C11.

The Contractor may apply in writing for Provisional Acceptance only after completion of all contractual obligations required up to the date of Provisional Acceptance.

Provisional Acceptance may be granted only if all of the following conditions have been fulfilled to the satisfaction of the Contracting Authority:

(a) delivery of the equipment to the place of acceptance;

(b) unloading and installation of the equipment;

(c) completion of Mechanical Commissioning;

(d) completion of Electrical and Control Commissioning;

(e) successful completion of Functional Testing;

(f) successful completion of Performance Testing demonstrating compliance with all minimum performance requirements specified in Annex II – Technical Specifications;

(g) successful completion of the Site Acceptance Test (SAT);

(h) completion of operator and maintenance training;

(i) submission of all contractual documentation, including manuals, drawings, certificates, declarations of conformity, warranty documents and spare parts catalogues;

(j) submission of the Certificate of Origin, where applicable;

(k) remedy of all critical defects and deficiencies affecting the safe operation, functionality or contractual compliance of the equipment.

Provisional Acceptance shall not be granted where any Category A (Critical) or Category B (Major) deficiencies remain outstanding.

Conditional Provisional Acceptance may only be granted where the outstanding deficiencies are classified exclusively as Category C (Minor) deficiencies and do not affect safety, functionality, contractual performance or operational use of the equipment.

The Contracting Authority shall, within forty-five (15) calendar days of receipt of the Contractor's application for Provisional Acceptance, either:

(i) issue the Certificate of Provisional Acceptance, stating, where appropriate, any minor deficiencies or outstanding items that do not materially affect the safe operation and intended use of the equipment; or

(ii) reject the application, giving reasons and specifying the measures required for Provisional Acceptance to be granted.

The issuance of the Certificate of Provisional Acceptance shall not release the Contractor from any warranty obligations, technical support obligations or liabilities arising under the Contract.

Failure of the Contracting Authority to issue the Certificate of Provisional Acceptance or to communicate a reasoned rejection within the above period shall not constitute deemed acceptance but shall require the Contracting Authority to promptly justify the delay and proceed with the acceptance procedure without undue delay.

The Contracting Authority may refuse Provisional Acceptance where:

(a) the equipment fails to comply with Annex II – Technical Specifications;

(b) the equipment fails to successfully complete the Site Acceptance Test (SAT);

(c) the equipment fails to achieve the minimum performance requirements specified in Annex II – Technical Specifications;

(d) required contractual documentation has not been submitted;

(e) critical defects or deficiencies remain outstanding.

Minor deficiencies and outstanding items that do not materially affect the safe operation and intended use of the equipment may be recorded in the Certificate of Provisional Acceptance and shall be remedied by the Contractor within a period specified by the Contracting Authority.

The Certificate of Provisional Acceptance shall constitute the contractual milestone for the first payment of ninety per cent (90%) of the Contract Price in accordance with Article 26.

For the purposes of this Contract, the date of Provisional Acceptance shall constitute the reference date for the commencement of the warranty period and the calculation of all contractual periods linked to the availability of spare parts and after-sales services.

Article 32	Warranty obligations

32.6	By way of commercial warranty and without prejudice to the provisions of the General Conditions, the Contractor warrants that the supplied equipment, including all components, systems, accessories and ancillary equipment, shall be free from defects in design, materials and workmanship and shall conform to the requirements of the Contract and Annex II – Technical Specifications.

During the warranty period, the Contractor shall, at its own cost and without undue delay:

(a) repair or replace any defective equipment, component, spare part or accessory;

(b) provide all labour, tools, equipment, transport, travel and accommodation necessary for warranty interventions;

(c) provide all replacement parts, consumables and materials required for the correction of defects resulting from design, manufacturing or installation deficiencies;

(d) correct any software, control system or configuration defects and provide software or firmware updates necessary to restore the proper functioning of the equipment, where applicable;

(e) provide technical support and troubleshooting assistance.

The Contractor shall acknowledge any warranty notification within forty-eight (48) hours of receipt.

Where the defect cannot be resolved remotely, the Contractor shall mobilise appropriately qualified service personnel and commence on-site intervention within five (5) working days following notification by the Contracting Authority.

All repairs and replacements carried out under warranty shall be performed without additional cost to the Contracting Authority.

The Performance Guarantee shall be released in accordance with Article 11 of these Special Conditions following fulfilment of all contractual obligations.

Any component repaired or replaced under warranty shall be covered by the warranty for the remainder of the original warranty period or for six (6) months from the date of repair or replacement, whichever period is longer.

The Contractor shall ensure the availability of spare parts and technical support services for a minimum period of five (5) years following the date of Provisional Acceptance.

The warranty period shall be suspended for any period during which the equipment is unavailable for operation due to defects covered by the warranty and shall be extended by a period equal to the duration of such unavailability.

32.7	The warranty must remain valid for twelve (12) months after the date of Provisional Acceptance or until the equipment has accumulated one thousand five hundred (1,500) operating hours, whichever occurs later.

Article 33	After-sales service

33.1	Without prejudice to the warranty obligations set out in Article 32, the Contractor shall ensure the availability of after-sales services and technical support for a minimum period of five (5) years following the date of Provisional Acceptance.

The after-sales service shall include, as a minimum:

(a) availability of appropriately qualified service personnel;

(b) availability of technical advice and troubleshooting assistance;

(c) availability of spare parts and consumables;

(d) availability of maintenance services, including preventive maintenance services upon request;

(e) availability of software and firmware support, where applicable;

(f) availability of remote technical support, where applicable.

The Contractor shall provide, for information purposes only, an itemised indicative price list of recommended spare parts and consumables and indicative service rates for after-sales services in accordance with the Tender Dossier.

The provision of after-sales services beyond the warranty obligations set out in Article 32 shall be performed only upon request of the Contracting Authority and shall be subject to separate orders or arrangements outside the scope of this Contract.

No proportion of the Performance Guarantee shall be assigned to after-sales service obligations under this Article.

Article 40	Settlement of disputes

Any dispute arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the courts of the Republic of North Macedonia in accordance with its national legislation.

The jurisdiction conferred under this clause is exclusive and any jurisdiction under a bilateral or multilateral investment treaty, or under the rules of the International Centre for Settlement of Investment Disputes (ICSID), is expressly excluded.

Article 44	Data protection

[For the purpose of Article 44 of the general conditions, for the part of the data transferred by the contracting authority to the European Commission:

(a)	the controller for the processing of personal data carried out within the Commission is the head of contracts and finance unit R4 of DG Neighbourhood and Enlargement Negotiations (DG NEAR)

(b)	the privacy statement is available at https://wikis.ec.europa.eu/display/ExactExternalWiki/Annexes#Annexes-AnnexesA(Ch.2):General]

1.	Processing of personal data related to the implementation of the contract by the contracting authority takes place in accordance with the national legislation of the state of the contracting authority and with the provisions of the respective financing agreement.

2.	To the extent that the contract covers an action financed by the European Union, the Contracting Authority may share communications related to the implementation of the contract, with the European Commission. These exchanges shall be made to the Commission, solely for the purpose of allowing the latter to exercise its rights and obligations under the applicable legislative framework and under the financing agreement with the Partner country – contracting authority. The exchanges may involve transfers of personal data (such as names, contact details, signatures and CVs) of natural persons involved in the implementation of the contract (such as contractors, personnel, experts, trainees, subcontractors, insurers, guarantors, auditors and legal counsel). In cases where the contractor is processing personal data in the context of the implementation of the contract, he/she shall accordingly inform the data subjects of the possible transmission of their data to the Commission. When personal data is transmitted to the Commission, the latter processes them in accordance with Regulation (EU) 2018/1725 of the European Parliament and of the Council of 23 October 2018 on the protection of natural persons with regard to the processing of personal data by the Union institutions, bodies, offices and agencies and on the free movement of such data, and repealing Regulation (EC) No 45/2001 and Decision No 1247/2002/EC and as detailed in the specific privacy statement published at ePRAG.

- Article 45	Further additional clauses

- The supplied equipment shall be fitted with a non-resettable and tamper-proof operating hours meter capable of recording the total accumulated operating hours of the equipment. The operating hours meter shall constitute the sole contractual reference for determining the operating hours accumulated for the purposes of warranty administration under Article 32.

- +All documentation, manuals, certificates, training materials and operational instructions required under the Contract shall be provided in English and Macedonian language.

- * * *

European Commission, Communication and Visibility Requirements for EU-funded External Actions:
https://international-partnerships.ec.europa.eu/knowledge-hub/communicating-and-raising-eu-visibility-guidance-external-actions_en

DDP (Delivered Duty Paid - Incoterms 2020 International Chamber of Commerce - http://www.iccwbo.org/incoterms/

OJ L 205 of 21.11.2018, p. 39