# ANNEX II + III:	 TECHNICAL SPECIFICATIONS + TECHNICAL OFFER

Contract title: “Supply, Delivery, Installation, Commissioning and Training for One (1) Mobile Jaw Crusher Machine with an Integrated Picking Station for the Re-use and Management of Construction and Demolition Waste”

p 1 /…

Publication reference:  RE-CONSTRUCT/IPA/2026/SUP/T01

Columns 1-2 should be completed by the contracting authority

Columns 3-4 should be completed by the tenderer

Column 5 is reserved for the evaluation committee

Annex III - the contractor's technical offer

The tenderers are requested to complete the template on the next pages:

- Column 2 is completed by the contracting authority shows the required specifications (not to be modified by the tenderer),

- Column 3 is to be filled in by the tenderer and must detail what is offered (for example the words ‘compliant’ or ‘yes’ are not sufficient)

- Column 4 allows the tenderer to make comments on its proposed supply and to make eventual references to the documentation

The eventual documentation supplied should clearly indicate (highlight, mark) the models offered and the options included, if any, so that the evaluators can see the exact configuration. Offers that do not permit to identify precisely the models and the specifications may be rejected by the evaluation committee.

The offer must be clear enough to allow the evaluators to make an easy comparison between the requested specifications and the offered specifications.

| 1. Item number | 2. Specifications required | 3. Specifications offered | 4. Notes, remarks, ref to documentation | 5. Evaluation committee’s notes |
| --- | --- | --- | --- | --- |
| 1 | Jaw crusher machine- with specifications described in below sub-section |  |  |  |
| 1.1 | Capacity of processing : - min 50 t/Hour - up to - 250 t/hour |  |  |  |
| 1.2 | Applied crushing technology : - Eccentric plates and jaw housing made of improved, abrasion-resistant steel |  |  |  |
| 1.3 | Drive unit : - Diesel engine |  |  |  |
| 1.4 | Total installed capacity of the plant: - Up to 400 KW |  |  |  |
| 1.5 | Input technology and size capacity: - Integrated picking station i.e. vibrating frame for receiving CDW 120mm - 250mm |  |  |  |
| 1.6 | Output granulation capacity: Adjustable from 10mm-40mm |  |  |  |
| 1.7 | Mobility: - Independent movement of rubber tracks driven by hydraulic drive; or - Forced propulsion with integrated tow-bar, axles and wheels |  |  |  |
| 1.8 | Safety and quality : - Mandatory certificates of conformity ISO 9001:2015 and CE |  |  |  |
| 1.9 | Material separation technology: - Integrated magnetic separator with conveyor belt for separating metals |  |  |  |
| 1.10 | Material for processing: - Reinforced concrete fractions and slabs, marble, granite, ceramics, stone, cement materials, clay materials (tiles, bricks), gypsum, etc. |  |  |  |
| 1.11 | Dust protection technology: - Integrated water sprinklers |  |  |  |
| 1.12 | Processed material transportation: - Integrated belt conveyor |  |  |  |
| 1.13 | Warranty and After-Sales Service* The Contractor shall provide: (a) a minimum warranty period of twelve (12) months or 1,500 operating hours, whichever occurs later; (b) warranty service covering the repair or replacement of defective parts, components and workmanship at no additional cost to the Contracting Authority; (c) technical support during the warranty period, including remote assistance and on-site interventions where necessary; (d) Warranty support shall be provided in accordance with the following minimum response times: - Critical Failure (equipment completely inoperable or unable to perform its intended function): response within forty-eight (48) hours; - Major Failure (significant reduction of operational performance but equipment remains partially operational): response within five (5) calendar days; - Minor Failure (defects not materially affecting the operation of the equipment): response within ten (10) calendar days. The response may initially be provided remotely where appropriate, however, where remote intervention does not resolve the malfunction, the Contractor shall provide on-site intervention within the same response periods. (e) availability of spare parts and consumables for a minimum period of five (5) years following Provisional acceptance of the equipment. |  |  |  |
| 1.14 | Documentation User Manual: The supplier must provide comprehensive user manuals, including maintenance schedules. The User Manuals should be translated into Macedonian language as well. |  |  |  |
| 1.15 | Delivery and Installation ** - Site Acceptance Test (SAT) - The machine should be delivered and installed to the designated site. - Training for operators and maintenance personnel must be provided by the supplier upon delivery. The trainings will be held on Macedonian language |  |  |  |

*For the avoidance of doubt, the following distinction shall apply between warranty services and after-sales services:

| Obligation | Warranty Service | After-Sales Service |
| --- | --- | --- |
| Repair of defects | Included | Not included |
| Replacement of defective parts | Included | Not included |
| Technical support during warranty | Included | Not included |
| Supply of spare parts after warranty | Not applicable | Included |
| Technical advice after warranty | Not applicable | Included |
| Availability of service technicians | Not applicable | Included |
| Remote troubleshooting after warranty | Not applicable | Included |
| Preventive maintenance services | Not applicable | Available upon request and at additional cost |
| Training refreshers | Not applicable | Optional |
| - Software/firmware updates (if applicable) | As required under warranty terms | Included where available |

- After-sales services following expiry of the warranty period shall be available on a commercial basis unless otherwise expressly specified in the Technical Specifications.

The engineering sequence described below represents the minimum contractual acceptance sequence. The Contractor may organise its internal implementation activities differently provided that the contractual sequence and dependencies established herein are respected.

**1.15 Delivery and Installation

# Delivery;

# Unloading;

# Installation;

  - Pre-SAT Readiness Verification

# Engineering Acceptance Activities;

5.1 Mechanical Inspection and Commissioning

- Assembly and installation of the crusher and integrated picking station.

- Installation of conveyors, magnetic separator, dust suppression system, hydraulic systems, etc.

- Inspection of all components and connections.

5.2 Electrical and Control Inspection and Commissioning

- Start-up of the diesel engine and electrical systems.

- Verification of sensors, control panels and emergency stop systems.

- Calibration of operating parameters.

5.3 Safety Inspection

5.4 Functional Testing

- Dry-run testing (without material).

- Testing of all moving components.

- Verification of safety systems and alarms.

5.5 Performance Testing and Site Acceptance Test (SAT)

"Site Acceptance Test (SAT)" means the contractual testing procedure performed following successful completion of Performance Testing in order to verify the complete operational readiness and conformity of the equipment with the Contract.

Performance testing shall be performed using actual construction and demolition waste supplied by the Contracting Authority and shall demonstrate compliance with all minimum performance requirements specified in Annex II – Technical Specifications.

- Demonstrating the minimum processing capacity and operational performance requirements specified in Annex II – Technical Specifications.

- Verifying output granulation

- Verifying operation of:

- integrated picking station;

- magnetic separator;

- conveyor belts;

- water sprinklers;

- mobility system.

5.6 Site Acceptance and Provisional Acceptance Procedure

The Acceptance Testing phase shall verify that the equipment, its installation and all associated services comply fully with the requirements of the Contract, Annex II – Technical Specifications and all applicable standards.

The Acceptance Testing activities shall include, as a minimum:

- verification of successful completion of Mechanical, Electrical and Functional Commissioning;

- verification of successful completion of Performance Testing using actual construction and demolition waste supplied by the Contracting Authority;

- verification of successful completion of the Site Acceptance Test (SAT);

- verification of the submission of all required documentation, manuals, certificates and records;

- verification of completion of all required operator and maintenance training activities;

- completion and signature of the SAT Engineering Acceptance Report (SAT EAR), incorporating the inspection records, testing records, performance verification records, Deficiency Register and Committee Recommendation, together with all other acceptance documentation required under the Contract;

- Recommendation to the Contracting Authority for the issue of the Certificate of Provisional Acceptance (C11A).

The acceptance process shall be carried out in the following sequence:

a) Completion of Delivery and Installation;
(b) Pre-SAT Readiness Verification;
(c) Mechanical Inspection and Commissioning;
(d) Electrical and Control Inspection and Commissioning;
(e) Safety Inspection;
(f) Functional Testing;
(g) Performance Testing;
(h) Site Acceptance Test (SAT);
(i) Committee Recommendation;
(j) Issue of the Certificate of Provisional Acceptance (C11A);
(k) Correction of deficiencies, where applicable;
(l) Final Acceptance (C11B).

No payment milestone, acceptance certificate or commencement of the warranty period shall occur before successful completion of all preceding stages.

Failure to demonstrate compliance with the minimum performance requirements specified in Annex II – Technical Specifications, failure to successfully complete the Performance Testing or failure to successfully complete the Site Acceptance Test (SAT) shall entitle the Contracting Authority to refuse Provisional Acceptance and require corrective actions, additional testing and re-testing at the Contractor's sole cost and risk.

Provisional Acceptance of the equipment shall not be granted solely upon delivery and installation. Provisional Acceptance shall be granted only after:

(a) successful completion of the engineering inspections, commissioning activities, Functional Testing, Performance Testing and the Site Acceptance Test (SAT), in accordance with the SAT Engineering Acceptance Report (SAT EAR);

(b) submission of all contractual documentation;

(c) completion of all required operator and maintenance training;

(d) confirmation that no Category A (Critical)deficiencies remain outstanding.

# Operator training;

Training operators and maintenance personnel in Macedonian language. Training shall consist of:
(a) operator training;
(b) routine maintenance training;
(c) safety training;
(d) emergency procedures;
(e) daily inspection procedures.

# Warranty service;

# Technical support during warranty;

# Documentation and manuals.