# Annex VI – Work Plan

Colour legend: Contractual (Green) | Technical (Blue) | Acceptance (Yellow) | Financial (Pink)

| Category | Activity | Abb. | Cross-reference | Deadline | Cumulated Day | Date |
| --- | --- | --- | --- | --- | --- | --- |
| Contractual | Commencement Order | CO | SC Art.18 | Award+90 | 1 | (1) |
| Contractual | Delivery Order | DO | GC Art.29 | D-10 | 81 | (3) |
| Technical | Delivery to Place of Acceptance | D | SC Art.19 | CO+60 | 61 | (3) |
| Technical | PTA | PTA | SC Art.25 | D+2 | 63 | (3) |
| Technical | Mechanical Inspection and Commissioning | MC | SC Art.25 | PTA+7 | 70 | (3) |
| Technical | Electrical and Control Inspection and Commissioning | ECC | SC Art.25 | MC+5 | 75 | (3) |
| Technical | Functional Testing | FT | SC Art.25 | ECC+3 | 78 | (3) |
| Technical | Performance Testing | PT | SC Art.25 | FT+4 | 82 | (3) |
| Acceptance | Site Acceptance Test | SAT | SC Art.25 | PT+3 | 85 | (3) |
| Acceptance | Submission of SAT EAR and Request for Provisional Acceptance | RPA | GC Art.31 | SAT+1 | 86 | (3) |
| Acceptance | Provisional Acceptance | PA | GC Art.31 | CO+90 | 91 | (2) |
| Acceptance | Deficiency Correction Period | DCP | SC Art.19 | PA+30 | 121 | (2) |
| Acceptance | Final Acceptance | FA | SC Arts.26/31 | After DCP | 121 | (2) |
| Financial | 90% Payment | P1 | SC Art.26 | After PA | 91 | (4) |
| Financial | 10% Payment | P2 | SC Art.26 | After FA | 121 | (4) |
| Contractual | End of Warranty | EW | SC Art.32 | PA+365 | 456 | (4) |
| Contractual | Release of Performance Guarantee | RPG | GC Art.11 | EW+60 | 516 | (5) |

## Indicative Gantt Timeline

| Phase | Start | Finish | Duration | Reference | Remarks |
| --- | --- | --- | --- | --- | --- |
| Implementation Activities (Delivery, Transport & Installation) | 1 | 60 | 60 days | Art.19 | DDP |
| Engineering Inspection, Commissioning & Functional Testing | 61 | 78 | 18 days | Art.25 | Mechanical Inspection and Commissioning Electrical and Control Inspection and Commissioning |
| Performance Testing | 79 | 82 | 4 days | Art.25 | C&D waste |
| SAT | 83 | 85 | 3 days | Art.25 | Acceptance verification – technical. Completed SAT EAR |
| Review and Issue of Provisional Acceptance (C11A) | 86 | 90 | 5 | Art.25 | Acceptance verification - administrative/contractual- Certificate |
| Deficiency Correction | 92 | 121 | Up to 30 days | Art.19 | If required |
| Final Acceptance | 121 | 121 | 1 day | Arts.26/31 | 10% payment |
| Warranty | 91 | 456 (variable) | 365 days | Art.32 | Starts from PA. 12 months or 1,500 operating hours (whichever occurs later) |

## Cross-reference Summary

Article 19 – Implementation Period (90 + 30 days).

Article 25 – Commissioning, Performance Testing and SAT.

Article 26 – Payment Milestones (90% / 10%).

Article 31 – Provisional and Final Acceptance.

Article 32 – Warranty Period.

The implementation period is 90 calendar days and includes delivery, installation, commissioning, Performance Testing, completion of the Site Acceptance Test (SAT) and all activities necessary to enable the issue of the Certificate of Provisional Acceptance.

A deficiency correction period of up to 30 calendar days may be granted where deficiencies are identified.

Successful completion of tests does not by itself constitute Provisional Acceptance.

The first payment of 90% becomes due only upon issuance of the Certificate of Provisional Acceptance.

The final payment of 10% becomes due only after completion of all deficiency correction obligations and After Final Acceptance.

- The activities shown in the Work Plan represent the minimum contractual sequence. The Contractor may organize its internal activities differently provided that the contractual milestones, dependencies and completion dates are respected.

- Actual date of Commencement order

- The deadline set here is the final deadline, set by the Contracting Authority, when all verification operations must be executed in order to finish the implementation in accordance with the contract.

- Distribution of days for each activity within the verification operations period shall be agreed with the Contractor.

- To be communicated by the Contracting Authority based on the actual date of the Provisional Acceptance

- Subject to fulfilment of all contractual obligations. Performance guarantee shall be released within 60 days of the actual date of the Final Acceptance.

NOTE: All deadlines except the end of warranty period are final deadlines on which relevant activity must be executed, meaning that activities can be executed earlier which will be reflected in the updated Programme of implementation of tasks. Only the warranty shall remain valid for exactly one year after provisional acceptance as stipulated in Article 32 of the Special Conditions.