# Annex VII – Work Plan

RE-CONSTRUCT/IPA/2026/SUP/T02

One (1) Hydraulic Crawler Excavator with Hydraulic Breaker for Re-use and Management of Construction and Demolition Waste.

| Category | Activity | Abb. | Cross-reference | Deadline | Cumulated Day | Date |
| --- | --- | --- | --- | --- | --- | --- |
| Technical | Delivery to Place of Acceptance | D | SC Art. 19 | CO+60 | 61 | (1) |
| Technical | Delivery Inspection | DI | SC Art. 31 / Annex VI Form A | D+1 | 62 | (3) |
| Technical | Commissioning | COM | SC Art. 31 / Annex VI Form B | D+2 | 63 | (3) |
| Technical | Operational Test | OT | SC Art. 31 / Annex VI Form C | D+3 | 64 | (3) |
| Technical | Operator & Maintenance Training | TR | SC Art. 31 / Annex VI Form D | D+4 | 65 | (3) |
| Acceptance | Submission of Request for Provisional Acceptance | RPA | SC Art. 31 | D+5 | 66 | (3) |
| Acceptance | Review by Acceptance Commission | RAC | SC Art. 31 | RPA+5 | 71 | (3) |
| Acceptance | Provisional Acceptance | PA | SC Art. 31 | CO+90 | 91 | (3) |
| Acceptance | Deficiency Correction Period | DCP | SC Art.19 | PA+30 | 121 | (2) |
| Acceptance | Final Acceptance | FA | SC Arts.26/31 | After DCP | 121 | (2) |
| Financial | 90% Payment | P1 | SC Art.26 | After PA | 91 | (4) |
| Financial | 10% Payment | P2 | SC Art.26 | After FA | 121 | (4) |
| Contractual | End of Warranty | EW | SC Art.32 | PA+365 | 456 | (4) |
| Contractual | Release of Performance Guarantee | RPG | GC Art.11 | EW+60 | 516 | (5) |
|  | ## Abb. - Abbreviations: ## CO – Commencement Order. ## DI - Delivery Inspection ## COM – Commissioning ## OT - Operational Test ## TR - Training ## RPA - Request for Provisional Acceptance ## RAC - Review by Acceptance Commission ## PA - Provisional Acceptance ## FA - Final Acceptance Colour legend: Technical (Blue) ¦ Acceptance (Yellow) ¦ Financial (Pink) |  |  |  |  |  |

## Indicative Contract Implementation Schedule

| Phase | Start | Finish | Duration | Reference | Remarks |
| --- | --- | --- | --- | --- | --- |
| Implementation Activities (Delivery, Transport & Installation) | 1 | 60 | 60 days | Art.19 | DDP |
| Delivery Inspection | 61 | 62 | 1 day | Art.31 | Verification of delivery, documentation and condition |
| Commissioning | 63 | 63 | 1 day | Art.31 | Machine prepared for operation |
| Operational Test | 64 | 64 | 1 day | Art.31 | Demonstration under operating conditions |
| Operator & Maintenance Training | 65 | 65 | 1 day | Art.31 | Practical training completed |
| Review and Issue of Provisional Acceptance (C11A) | 66 | 90 | Up to 25 days | Art.31 | Administrative verification and certificate |
| Deficiency Correction | 92 | 121 | Up to 30 days | Art.31 | Only where deficiencies exist |
| Final Acceptance | 121 | 121 | 1 day | Arts.26/31 | Final acceptance certificate |
| Warranty | 91 | 456 (variable) | 365 days | Art.32 | Starts from PA. 12 months or 1,500 operating hours (whichever occurs later) |

## Cross-reference Summary

Article 19 – Implementation Period (90 calendar days, plus up to 30 calendar days for correction of deficiencies where applicable).

Article 26 – Payment Milestones (90% / 10%).

Article 31 – Delivery Inspection, Commissioning, Operational Test and Acceptance Procedures.

Article 32 – Warranty Period.

The implementation period includes delivery, installation, commissioning, operational testing, operator and maintenance training and all activities necessary for the issue of the Certificate of Provisional Acceptance.

A deficiency correction period of up to 30 calendar days may be granted where deficiencies are identified.

Successful completion of tests does not by itself constitute Provisional Acceptance.

The first payment of 90% becomes due only upon issuance of the Certificate of Provisional Acceptance.

The final payment of 10% becomes due only after completion of all deficiency correction obligations and issuance of the Final Acceptance Certificate.

- The activities shown in the Work Plan represent the minimum contractual sequence. The Contractor may organize its internal activities differently provided that the contractual milestones, dependencies and completion dates are respected.

- Actual date of Commencement order

- The deadline set here is the final deadline, set by the Contracting Authority, when all verification operations must be executed in order to finish the implementation in accordance with the contract.

- Distribution of days for each activity within the verification operations period shall be agreed with the Contractor.

- To be communicated by the Contracting Authority based on the actual date of the Provisional Acceptance

- Subject to fulfilment of all contractual obligations. Performance guarantee shall be released within 60 days of the actual date of the Final Acceptance.

NOTE: All deadlines except the end of warranty period are final deadlines on which relevant activity must be executed, meaning that activities can be executed earlier which will be reflected in the updated Programme of implementation of tasks. Only the warranty shall remain valid for exactly one year after provisional acceptance as stipulated in Article 32 of the Special Conditions.